## Risk Register
AVC Risk Register
ID | Phase | Risk Name | Risk Statement (Cause → Risk → Impact) | Category | Likelihood | Impact | Score | Priority | Primary Mitigations | Contingency / Response Plan | Owner | Triggers / Early Warnings | Status | Client-Facing | AI-IRB Flag | Date Identified | Last Reviewed | Notes / History
↓ Enter new risks below. See 'Sample Risks' tab for examples and 'Instructions' tab for process guidance.
0

## Sample Risks
Sample Risks - Copy relevant risks to the Risk Register tab and customize
ID | Phase | Risk Name | Risk Statement (Cause → Risk → Impact) | Category | Likelihood | Impact | Score | Priority | Primary Mitigations | Contingency / Response Plan | Owner | Triggers / Early Warnings | Status | Client-Facing | AI-IRB Flag | Date Identified | Last Reviewed | Notes / History
R-ONB-01 | Onboarding | Incomplete sales handoff | If sales-to-delivery handoff is incomplete, then delivery team lacks critical context → mis-scoped onboarding → rework + timeline slip. | Process | 4 | 4 | 16 | High | Standard handoff checklist; mandatory handoff meeting; attach SOW, assumptions, exclusions, key stakeholders. | Escalate to account owner; re-baseline timeline; conduct rapid discovery workshop. | Onboarding Lead | Missing SOW artifacts; unclear success metrics; >10 open items after kickoff. | Open | Yes | No
R-ONB-02 | Onboarding | Vague acceptance criteria | If SOW/SLA acceptance criteria are vague, then expectations diverge → scope disputes → delayed sign-off. | Commercial | 3 | 5 | 15 | High | Acceptance criteria template; convert promises into measurable outputs; contract translation review. | Formal change request; negotiate revised criteria; executive sponsor alignment call. | Delivery Manager | Frequent 'that's not what we meant' comments; no single source of truth. | Open | Yes | No
R-ONB-03 | Onboarding | Client access delays | If client delays access/credentials/data, then setup stalls → onboarding slips → missed go-live. | Client | 5 | 4 | 20 | High | Day-0 access packet; named client IT owner; automated reminders; access gates tied to timeline. | Parallelize work; propose sandbox data; escalate to client sponsor. | Onboarding Lead | Access tickets idle >3 days; repeated 'waiting on IT'; missing data fields. | Open | Yes | No
R-ONB-04 | Onboarding | Late security review | If security/privacy review starts late, then approval delays → blocked data transfer → onboarding stalls. | Compliance | 4 | 5 | 20 | High | Trigger security package at contract stage; pre-approved security docs; dedicated security contact. | Phased rollout with non-sensitive data; re-sequence tasks; exec escalation. | Security/Compliance | Security questionnaire arrives after kickoff; unanswered questions >5 days. | Open | Yes | Yes
R-ONB-05 | Onboarding | Rushed discovery | If discovery is rushed or stakeholders unavailable, then requirements are incomplete → wrong configuration → rework. | Process | 4 | 4 | 16 | High | Structured discovery agenda; required stakeholder list; RACI; written requirement confirmation. | Discovery 2.0 workshop; update scope and timeline; document as change log. | Implementation PM | Key stakeholder misses kickoff; late 'we forgot to mention'; priority reversals. | Open | Yes | No
R-FUL-01 | Fulfillment | Capacity overload | If effort is underestimated and capacity planning is weak, then team overload → delivery delays + burnout. | Resourcing | 4 | 4 | 16 | High | Capacity model; intake limits; staffing buffer for 60-90 days; track utilization. | Reprioritize backlog; add contractors; renegotiate deliverable dates. | Delivery Manager | Utilization >85% sustained; deadlines slip; rising defect rate. | Open | No | No
R-FUL-02 | Fulfillment | Brittle integrations | If integrations/automations are brittle, then failures go unnoticed → silent data breaks → incorrect outputs. | Technology | 4 | 5 | 20 | High | Monitoring + alerts; retries/idempotency; validation checks; staged rollouts; integration tests. | Switch to manual process; roll back release; communicate incident to client. | Tech Lead | Data freshness gaps; job failures; exception spikes; unexplained KPI swings. | Open | Yes | No
R-FUL-03 | Fulfillment | Weak QA gates | If QA gates are weak, then defects reach client → trust erosion + rework. | Quality | 4 | 4 | 16 | High | Definition of Done; peer review; sampling audits; automated tests; validation checklist. | Hotfix workflow; client incident comms; root cause analysis. | QA/Delivery Lead | Increasing support tickets; repeated corrections; missed acceptance checks. | Open | Yes | No
R-FUL-04 | Fulfillment | Uncontrolled scope creep | If change requests aren't controlled, then scope creeps → timeline/budget overrun. | Commercial | 4 | 4 | 16 | High | Change control policy; impact assessments; 'out of scope' log; client approval before work. | Pause non-critical work; renegotiate SOW; add paid change order. | Account Manager | Frequent 'small tweaks'; backlog grows faster than throughput. | Open | Yes | No
R-XCT-01 | Both | Unclear roles/RACI | If roles/responsibilities are unclear, then work falls through cracks → missed tasks → SLA/quality issues. | People | 4 | 4 | 16 | High | Publish RACI; single-threaded owner per workstream; weekly governance; decision log. | Escalate to sponsor; reassign ownership; add interim PM support. | Delivery Ops | Duplicate work; no owner in meetings; unresolved actions >1 week. | Open | No | No
R-XCT-02 | Both | Compliance mishandling | If compliance obligations (PII, SOC2, GDPR) are mishandled, then violations occur → legal + reputational damage. | Compliance | 3 | 5 | 15 | High | Least privilege; encryption; access reviews; audit trails; incident response plan. | Incident response activation; legal counsel; client notification; remediation plan. | Security/Compliance | Unapproved data sharing; unclear retention; audit findings. | Open | Yes | Yes
R-AI-01 | Fulfillment | Unmonitored model drift | If model drift is not monitored, then performance degrades silently → incorrect predictions → lost trust. | AI System | 4 | 4 | 16 | High | Drift detection dashboards; scheduled revalidation; alert thresholds; model versioning. | Retrain with updated data; roll back to previous version; communicate impact. | Data Science Lead | Accuracy declining; feature distribution shifts; user feedback issues. | Open | Yes | Yes
R-AI-02 | Fulfillment | Training data bias | If training data contains bias, then model outputs perpetuate inequities → ethical violations → reputational damage. | AI System | 3 | 5 | 15 | High | Bias audits pre-deployment; fairness metrics; diverse training data; explainability tools. | Pause model; conduct bias remediation; stakeholder communication; AI-IRB escalation. | AI-IRB Liaison | Fairness metrics degrading; complaints from user groups; audit findings. | Open | Yes | Yes

## Instructions
AVC Risk Register - Quick Reference
WHEN TO USE
• Create register at engagement kickoff
• Review weekly with delivery team
• Share High/Medium risks in client governance calls
ADDING A RISK
1. Assign ID (R-01, R-02, etc.)
2. Write short Risk Name (2-4 words)
3. Write Risk Statement: 'If [cause], then [risk] → [impact]'
4. Score Likelihood (1-5) and Impact (1-5)
5. Define mitigations and assign owner
SCORING
Likelihood: 1=Rare, 2=Unlikely, 3=Possible, 4=Likely, 5=Almost Certain
Impact: 1=Minor, 2=Moderate, 3=Major, 4=Severe, 5=Critical
Score = Likelihood × Impact
Priority: High (15-25), Medium (8-14), Low (1-7)
ESCALATION
• Score ≥20 or Priority=High → Notify Account Manager + AI-IRB Liaison
• AI-IRB Flag=Yes → AI-IRB review required before gate passage
• Blocked mitigation >5 days → Escalate to remove blocker
CLOSING A RISK
Status options: Open → Mitigating → Accepted or Closed
Document closure rationale in Notes column
High priority risks require Account Manager + AI-IRB sign-off to close
REFERENCE
See 'Sample Risks' tab for examples to copy and customize
See 'Scoring Reference' tab for detailed scoring definitions
Full process: SOP-1062-01-AI Risk Register Management

## Scoring Reference
Likelihood Scale
Score | Label | Definition
1 | Rare | Unlikely to occur; no historical precedent
2 | Unlikely | Could occur but not expected; few precedents
3 | Possible | May occur; some precedents or warning signs
4 | Likely | Probably will occur; multiple precedents or active warning signs
5 | Almost Certain | Expected to occur; currently occurring or imminent
Impact Scale
Score | Label | Definition
1 | Minor | Negligible effect on timeline, cost, or quality; easily absorbed
2 | Moderate | Some effect; requires adjustment but recoverable within sprint/phase
3 | Major | Significant effect; requires re-planning, client communication, or scope adjustment
4 | Severe | Serious effect; threatens milestone delivery, SLA breach, or client relationship
5 | Critical | Project-threatening; potential termination, compliance violation, or reputational damage
Priority Thresholds
Score Range | Priority | Required Response
15-25 | High | Immediate action required. Escalate to Account Manager and AI-IRB Liaison. Weekly review minimum.
8-14 | Medium | Active monitoring. Mitigations must be in place. Bi-weekly review minimum.
1-7 | Low | Monitor during standard reviews. Mitigations optional but recommended.

## Escalation Log
Date | Risk ID | Escalated By | Escalated To | Reason | Resolution | Resolution Date | Notes

## Client Summary
Risk ID | Phase | Risk Name | Priority | Status | Owner Role | Key Mitigation
(Copy High/Medium risks from main register where Client-Facing = Yes)